## Timeline
PI PROJECT MANAGEMENT
[10 empty] | w: working day o: off day | [23 empty] | w | [27 empty] | w | [13 empty] | w | [6 empty] | w | [69 empty] | w | [82 empty] | o |  |  | o | [7 empty] | o |  |  |  | w
[10 empty] | Week: | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 53 | 53 | 53 | 53 | 53 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 53 | 53
Day:
Project Name | Project Type | Progress | Detail Task | Plan Date Start | Plan Date Finished | Plan Working Days | Realization Date Start | Realization Date Finished | Realization Working Days | Status | 2026-01-01 | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28 | 2026-11-29 | 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05 | 2026-12-06 | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-12 | 2026-12-13 | 2026-12-14 | 2026-12-15 | 2026-12-16 | 2026-12-17 | 2026-12-18 | 2026-12-19 | 2026-12-20 | 2026-12-21 | 2026-12-22 | 2026-12-23 | 2026-12-24 | 2026-12-25 | 2026-12-26 | 2026-12-27 | 2026-12-28 | 2026-12-29 | 2026-12-30 | 2026-12-31 | 2027-01-01 | 2027-01-02 | 2027-01-03 | 2027-01-04 | 2027-01-05 | 2027-01-06 | 2027-01-07 | 2027-01-08 | 2027-01-09 | 2027-01-10 | 2027-01-11 | 2027-01-12 | 2027-01-13 | 2027-01-14 | 2027-01-15 | 2027-01-16 | 2027-01-17 | 2027-01-18 | 2027-01-19 | 2027-01-20 | 2027-01-21 | 2027-01-22 | 2027-01-23 | 2027-01-24 | 2027-01-25 | 2027-01-26 | 2027-01-27 | 2027-01-28 | 2027-01-29 | 2027-01-30 | 2027-01-31 | 2027-02-01 | 2027-02-02 | 2027-02-03 | 2027-02-04 | 2027-02-05 | 2027-02-06 | 2027-02-07 | 2027-02-08 | 2027-02-09 | 2027-02-10 | 2027-02-11 | 2027-02-12 | 2027-02-13 | 2027-02-14 | 2027-02-15 | 2027-02-16 | 2027-02-17 | 2027-02-18 | 2027-02-19 | 2027-02-20 | 2027-02-21 | 2027-02-22 | 2027-02-23 | 2027-02-24 | 2027-02-25 | 2027-02-26 | 2027-02-27 | 2027-02-28 | 2027-03-01 | 2027-03-02 | 2027-03-03 | 2027-03-04 | 2027-03-05 | 2027-03-06 | 2027-03-07 | 2027-03-08 | 2027-03-09 | 2027-03-10 | 2027-03-11 | 2027-03-12 | 2027-03-13 | 2027-03-14 | 2027-03-15 | 2027-03-16 | 2027-03-17 | 2027-03-18 | 2027-03-19 | 2027-03-20 | 2027-03-21 | 2027-03-22 | 2027-03-23 | 2027-03-24 | 2027-03-25 | 2027-03-26 | 2027-03-27 | 2027-03-28 | 2027-03-29 | 2027-03-30 | 2027-03-31 | 2027-04-01 | 2027-04-02 | 2027-04-03 | 2027-04-04 | 2027-04-05 | 2027-04-06 | 2027-04-07 | 2027-04-08 | 2027-04-09 | 2027-04-10 | 2027-04-11 | 2027-04-12 | 2027-04-13 | 2027-04-14 | 2027-04-15 | 2027-04-16 | 2027-04-17 | 2027-04-18 | 2027-04-19 | 2027-04-20 | 2027-04-21 | 2027-04-22 | 2027-04-23 | 2027-04-24 | 2026-12-30 | 2026-12-31
Default Timeline | Machine | #DIV/0! | Total Leadtime
Explain/Receive the Target/Goal
Discuss Target and Timeline
Checking Reference from Cosmax Group
Checking Target/Existing Product Specification (URS)
Pouch Bag Sealing Machine | Machine | 100% |  | 2026-07-30 | 2026-09-23 | 55 | 2026-07-30 | 2026-09-23 | 55 | DONE
|  |  | Cargo ready | 2026-07-30 | 2026-07-30 | 1 | 2026-07-30 | 2026-07-30 | 1
|  |  | Pick Up | 2026-08-03 | 2026-08-03 | 1 | 2026-08-03 | 2026-08-03 | 1 | Delayed due to Typhoon. First ETD Schedule was 11 Aug
|  |  | ETD Ningbo Port | 2026-09-05 | 2026-09-05 | 0 | 2026-09-03 | 2026-09-03 | 1
|  |  | Shipment by Sea. Ningbo - Jakarta | 2026-09-05 | 2026-09-13 | 5 | 2026-09-03 | 2026-09-13 | 7
|  |  | ETA Jakarta Port | 2026-09-13 | 2026-09-13 | 0 | 2026-09-13 | 2026-09-13 | 0
|  |  | Clearance | 2026-09-13 | 2026-09-16 | 3 | 2026-09-13 | 2026-09-16 | 3
|  |  | ETA Cosmax Indonesia | 2026-09-16 | 2026-09-16 | 1 | 2026-09-16 | 2026-09-16 | 1
|  |  | Machine Unboxing | 2026-09-16 | 2026-09-17 | 2 | 2026-09-16 | 2026-09-16 | 1
|  |  | Utility Installation | 2026-09-17 | 2026-09-18 | 2 | 2026-09-17 | 2026-09-18 | 2
|  |  | Engineer Flight WNZ-CGK | 2026-09-20 | 2026-09-20 | 0 | 2026-09-20 | 2026-09-20 | 0
|  |  | Technician Schedule for installation | 2026-09-21 | 2026-09-23 | 3 | 2026-09-21 | 2026-09-23 | 3
|  |  | Machine Validation | 2026-09-23 | 2026-09-23 | 1 | 2026-09-23 | 2026-09-23 | 1
|  |  | Engineer Flight CGK-WNZ | 2026-09-23 | 2026-09-23 | 1 | 2026-09-23 | 2026-09-23 | 1
Perfume Auto Filling Machine (90 days) | Machine | 0% |  | 2026-08-10 | 2027-01-22 | 165 |  |  |  | JUST PLANNING
|  |  | Mr. Go confirm proposal | 2026-08-10 | 2026-08-13 | 4
|  |  | RFA send | 2026-08-13 | 2026-08-13 | 1
|  |  | RFA approval | 2026-08-13 | 2026-08-24 | 8
|  |  | PO send | 2026-08-24 | 2026-08-24 | 1
|  |  | Deposit Payment | 2026-09-02 | 2026-09-02 | 1
|  |  | Machine Fabrication | 2026-09-02 | 2026-12-01 | 90
|  |  | FAT by Cosmax China | 2026-12-01 | 2026-12-07 | 5
|  |  | Payment Before Delivery | 2026-12-16 | 2026-12-16 | 1
|  |  | Cargo ready | 2026-12-21 | 2026-12-21 | 1
|  |  | Pick Up | 2026-12-22 | 2026-12-22 | 1
|  |  | ETD Shanghai Port | 2026-12-28 | 2026-12-28 | 1
|  |  | Shipment by Sea. Shanghai- Jakarta | 2026-12-28 | 2027-01-06 | 8
|  |  | ETA Jakarta Port | 2027-01-06 | 2027-01-06 | 1
|  |  | Clearance | 2027-01-06 | 2027-01-11 | 4
|  |  | ETA Cosmax Indonesia | 2027-01-11 | 2027-01-11 | 1
|  |  | Machine Unboxing | 2027-01-12 | 2027-01-12 | 1
|  |  | Utility Installation | 2027-01-13 | 2027-01-14 | 2
|  |  | Engineer Flight SHA-CGK | 2027-01-17 | 2027-01-17 | 0
|  |  | Technician Schedule for installation | 2027-01-18 | 2027-01-22 | 5
|  |  | Machine Validation | 2027-01-22 | 2027-01-22 | 1
|  |  | Engineer Flight CGK-SHA | 2027-01-22 | 2027-01-22 | 1
Perfume Auto Filling Machine (75 days) | Machine | 0% |  | 2026-08-10 | 2027-01-08 | 151 |  |  |  | JUST PLANNING
|  |  | Mr. Go confirm proposal | 2026-08-10 | 2026-08-13 | 4
|  |  | RFA send | 2026-08-13 | 2026-08-13 | 1
|  |  | RFA approval | 2026-08-13 | 2026-08-24 | 8
|  |  | PO send | 2026-08-24 | 2026-08-24 | 1
|  |  | Deposit Payment | 2026-09-02 | 2026-09-02 | 1
|  |  | Machine Fabrication | 2026-09-02 | 2026-11-16 | 75
|  |  | FAT by Cosmax China | 2026-11-16 | 2026-11-20 | 5
|  |  | Payment Before Delivery | 2026-12-02 | 2026-12-02 | 1
|  |  | Cargo ready | 2026-12-07 | 2026-12-07 | 1
|  |  | Pick Up | 2026-12-09 | 2026-12-09 | 1
|  |  | ETD Shanghai Port | 2026-12-14 | 2026-12-14 | 1
|  |  | Shipment by Sea. Shanghai- Jakarta | 2026-12-14 | 2026-12-23 | 8
|  |  | ETA Jakarta Port | 2026-12-23 | 2026-12-23 | 1
|  |  | Clearance | 2026-12-23 | 2026-12-28 | 4
|  |  | ETA Cosmax Indonesia | 2026-12-28 | 2026-12-28 | 1
|  |  | Machine Unboxing | 2026-12-29 | 2026-12-29 | 1
|  |  | Utility Installation | 2026-12-30 | 2026-12-31 | 2
|  |  | Engineer Flight SHA-CGK | 2027-01-03 | 2027-01-03 | 0
|  |  | Technician Schedule for installation | 2027-01-04 | 2027-01-08 | 5
|  |  | Machine Validation | 2027-01-08 | 2027-01-08 | 1
|  |  | Engineer Flight CGK-SHA | 2027-01-08 | 2027-01-08 | 1
Sheet Mask Cutting and Folding Machine | Machine | 0% |  | 2026-08-10 | 2026-12-22 | 134 |  |  |  | JUST PLANNING
|  |  | Mr. Go confirm proposal | 2026-08-10 | 2026-08-13 | 4
|  |  | RFA send | 2026-08-13 | 2026-08-13 | 1
|  |  | RFA approval | 2026-08-13 | 2026-08-19 | 5
|  |  | PO send | 2026-08-19 | 2026-08-19 | 1
|  |  | Deposit Payment | 2026-09-02 | 2026-09-02 | 1
|  |  | Machine Fabrication | 2026-09-02 | 2026-11-02 | 44
|  |  | Mid-Autumn Festival and National Day Holiday (China) | 2026-09-25 | 2026-10-07 | 9
|  |  | FAT by Cosmax Guangzhou | 2026-11-02 | 2026-11-06 | 5
|  |  | Payment Before Delivery | 2026-11-18 | 2026-11-18 | 1
|  |  | Cargo ready | 2026-11-23 | 2026-11-23 | 1
|  |  | Pick Up | 2026-11-25 | 2026-11-25 | 1
|  |  | ETD Shanghai Port | 2026-11-30 | 2026-11-30 | 1
|  |  | Shipment by Sea. Shanghai- Jakarta | 2026-11-30 | 2026-12-09 | 8
|  |  | ETA Jakarta Port | 2026-12-09 | 2026-12-09 | 1
|  |  | Clearance | 2026-12-09 | 2026-12-14 | 4
|  |  | ETA Cosmax Indonesia | 2026-12-14 | 2026-12-14 | 1
|  |  | Machine Unboxing | 2026-12-15 | 2026-12-15 | 1
|  |  | Utility Installation | 2026-12-16 | 2026-12-17 | 2
|  |  | Machine Validation | 2026-12-21 | 2026-12-22 | 2
TAT Cushion | Tooling NPD | 95% | Total Leadtime | 2026-08-24 | 2026-12-01 | 99 | 2026-08-24 | 0 | -46258 | ON PROGRESS
|  |  | Received RFA from MKT | 2026-08-24 | 2026-08-24 | 1 | 2026-08-24 | 2026-08-24 | 1
|  |  | Contact Keosan and Sobura for new Project Information | 2026-09-03 | 2026-09-03 | 1 | 2026-09-03 | 2026-09-03 | 1
|  |  | Request Sample to PRNI (Gita) via BM until received sample | 2026-09-03 | 2026-09-03 | 1 | 2026-09-03 | 2026-09-03 | 1
|  |  | Sending sample to Keosan | 2026-09-03 | 2026-09-03 | 1 | 2026-09-03 | 2026-09-03 | 1
|  |  | Waiting new quotation Keosan | 2026-09-03 | 2026-09-04 | 2 | 2026-09-03 | 2026-09-07 | 3
|  |  | Submit RFA | 2026-09-04 | 2026-09-08 | 3 | 2026-09-07 | 2026-09-21 | 11
|  |  | Send PO | 2026-09-22 | 2026-09-22 | 1 | 2026-09-22 | 2026-09-22 | 1
|  |  | Sending sample to Sobura | 2026-09-22 | 2026-09-22 | 1 | 2026-09-22 | 2026-09-22 | 1
|  |  | Leadtime Tooling Keosan | 2026-09-22 | 2026-10-07 | 12 | 2026-09-22 | 2026-10-09 | 14
|  |  | Leadtime Tooling Sobura | 2026-09-22 | 2026-10-07 | 12 | 2026-09-22 | 2026-10-09 | 14
|  |  | Validation | 2026-10-09 | 2026-10-09 | 1 | 2026-10-09 | 2026-10-09 | 1
|  |  | Target Launching Date | 2026-12-01 | 2026-12-01 | 1
UV Laser Coding | Machine | 43.75% | Total Leadtime | 2026-08-27 | 2026-10-29 | 63 | 2026-08-27 | 0 | -46261 | ON PROGRESS
|  |  | Mr. Go confirm proposal | 2026-08-27 | 2026-08-27 | 1 | 2026-08-27 | 2026-08-27 | 1
|  |  | RFA send | 2026-08-28 | 2026-08-28 | 1 | 2026-08-29 | 2026-08-29 | 0
|  |  | RFA approval | 2026-08-28 | 2026-09-03 | 5 | 2026-08-29 | 2026-09-22 | 17
|  |  | PO send | 2026-09-04 | 2026-09-04 | 1 | 2026-09-23 | 2026-09-23 | 1
|  |  | Payment | 2026-09-30 | 2026-09-30 | 1 | 2026-09-30 | 2026-09-30 | 1
|  |  | Machine Fabrication | 2026-09-30 | 2026-10-05 | 5 | 2026-09-30 | 2026-10-05 | 4
|  |  | Holiday (China) | 2026-10-01 | 2026-10-08 | 6 | 2026-10-01 | 2026-10-08 | 6
|  |  | CFS Closing | 2026-10-06 | 2026-10-06 | 1
|  |  | ETD Hongkong Port | 2026-10-11 | 2026-10-11 | 1
|  |  | Shipment by Sea. Hongkong- Jakarta | 2026-10-11 | 2026-10-17 | 5
|  |  | ETA Jakarta Port | 2026-10-17 | 2026-10-17 | 1
|  |  | Clearance | 2026-10-17 | 2026-10-21 | 4
|  |  | ETA Cosmax Indonesia | 2026-10-21 | 2026-10-21 | 1
|  |  | Machine Unboxing | 2026-10-22 | 2026-10-22 | 1
|  |  | Utility Installation | 2026-10-25 | 2026-10-26 | 2
|  |  | Machine Validation | 2026-10-28 | 2026-10-29 | 2
FFY Powder and Cream Blush | Tooling NPD | 37.5% | Total Leadtime | 2026-08-24 | 2026-12-02 | 100 | 0 | 0 | 0
|  |  | Fixed Price from MP | 2026-08-24 | 2026-08-28 | 5
|  |  | Proceed Godet | 2026-08-31 | 2026-09-11 | 10
|  |  | Revise Godet (without tulang) | 2026-09-14 | 2026-09-18 | 5
|  |  | Revise Godet (with tulang) | 2026-09-21 | 2026-09-25 | 5
|  |  | Lab Scale Tooling Process | 2026-10-05 | 2026-10-23 | 15
|  |  | CT | 2026-10-26 | 2026-10-30 | 5
|  |  | Start masspro (client) | 2026-10-26 | 2026-10-30 | 5
|  |  | Transfer from lab to production scale | 2026-11-02 | 2026-11-06 | 5
|  |  | Proceed Tooling Production | 2026-11-09 | 2026-12-09 | 23
|  |  | Received Actual Sample from PRNI | 2026-10-06 | 2026-10-06 | 1 | 2026-10-06 | 2026-10-06 | 1
|  |  | Target Delivery from Client | 2026-12-01 | 2026-12-02 | 2
DXN Lipstick Deboss Surface | Tooling NPD | #DIV/0! | Total Leadtime
NYK Kay Beauty Contour Stick | Tooling NPD | #DIV/0! | Total Leadtime
Lion Wings Press Powder | Tooling NPD | 100% | Total Leadtime | 2026-10-06 | 0 | -46301 | 2026-10-06 | 0 | -46301 | ON PROGRESS
|  |  | Resubmit RFA for Puncher only to send sample ASAP | 2026-10-06 | 2026-10-06 | 1 | 2026-10-06 | 2026-10-06 | 1
|  |  | Send PO | 2026-10-07 | 2026-10-07 | 1 | 2026-10-07 | 2026-10-07 | 1
|  |  | Send Sample | 2026-10-07 | 2026-10-07 | 1 | 2026-10-07 | 2026-10-07 | 1
|  |  | Tooling Fabrication | 2026-10-07 | 2026-10-21 | 11 | 2026-10-07 | 2026-10-21 | 11
Note on A1: Zahra Syahda COSMAX IDN: Legend: Grey: Weekend Yellow: Today Light Green: Plan Dark Green: Realization Light Blue: On Progress Green: DONE
Note on G52: Zahra Syahda COSMAX IDN: They can do 75 days calendar day, but still put 90 days as buffer
Note on G76: Zahra Syahda COSMAX IDN: They can do faster from standard 90 days tp 75 days calendar day
Note on I128: Zahra Syahda COSMAX IDN: Arrived at 7 Oct, Repair sent 8 Oct
Note on I129: Zahra Syahda COSMAX IDN: Arrived at 7 Oct, Repair sent 8 Oct
Note on A164: Zahra Syahda COSMAX IDN: 25,000 pcs PO 5,000 pcs per SKU, total 5 SKU
Note on A167: Zahra Syahda COSMAX IDN: 25,000 pcs PO 5,000 pcs per SKU, total 5 SKU
Note on A170: Zahra Syahda COSMAX IDN: 25,000 pcs PO 5,000 pcs per SKU, total 5 SKU